## Slide 1: LHC Injection and Dump Protection
W. Bartmann on behalf of the ABT team
LHC Beam Commissioning Workshop
Evian, 19-20 Jan 2010

## Slide 2: Commissioning Plan: Injection Protection
Calibration of BLMs
Centering/beam size of TCDIs and setting to 4.5 σ
Check phase space coverage
Check local MSI protection
TDI/TCLI centering/beam size and setting to ~7 σ
TDI/TCLI check against MKI failure

## Slide 3: TCDI set-up transfer line collimation
Centering OK for TI2 and TI8 TCDIs
Beam size: measured only for TCDIs upstream the TED, i.e. 2/6 per TL
Problems:
    normalization to intensity difficult because of poor BCT resolution in TL
    saturation of BLMs with fastest integration time scale
    crosstalk between BLMs
Set TCDIs to 4.5 σ: DONE for all TCDIs, but theoretical σ taken
Check phase space coverage: NOT done
Check local MSI protection: NOT done

## Slide 4: TDI and TCL set-up (I) vertical passive injection protection system
Set-up no major problem:
  Beam edge defined at 5.7 σ by collimation system
  few mm jaw asymmetry to understand for B2, beam well centered on adjacent BTVs
  TDI already protected LHC from overinjection or missing injection kick.
  Beam size at TDI NOT measured
upper jaw: +6 mm
lower jaw: -2 mm

## Slide 5: TDI and TCL set-up (II)
Losses and scraping studied, also with Beam Condition Monitors from LHCb and ALICE Problem:
  overinjection– now works for B1 but not B2 (losses on MQXA (Q3) R8 which triggers BLMs)

## Slide 6: Injection of 1 pilot bunch with TCDIs..
… at nominal 4.5 σ settings with losses from tails
(no SPS scraper):
Already close to BLM interlock limit for 40 μs integration time!
Beam 1
Beam 2

## Slide 7: Tail Scan with TCDIs
Tail Scan in TI2
Intensity: 1.2e11
Jaws set around derived beam centre
Jaw opening increased in steps
Very significant exponential beam tails…
  Scraping necessary?!?

## Slide 8: Injection with higher intensity
2e10 protons, with SPS scraping, 6 σ horizontal and 4.5 σ vertical collimator settings
very clean for B2
B1 has larger losses
Beam 1
Beam 2

## Slide 9: Commissioning Plan: Dump Protection
Correct orbit in point 6
TCDQ – check SW interlock on beam position wrt TCDQ position
Set up TCDQ/TCS jaws
Check of TCDQ protection
Calibration of beam loss signal and protons lost at TCDQ
Aperture in P6

## Slide 10: TCDQ/TCSG (I) protects Q4 and downstream elements
…in case of asynchronous beam dump or asynch. firing of MKD kickers where part of beam is not absorbed by TCDS
  TCDS (fixed) – 6 m long diluter protects extraction septum
  TCDQ/TCS (mobile) – 7 m long diluter kept at about 7-8 s from the beam, at all times

## Slide 11: TCDQ/TCSG set-up (II)
Centering of TCSG and TCDQ:
  DONE
  Problems:
    movement sense inversion for B2  solved (Mechanical inversion in tank)
    setting resolution of 0.1 mm, but change of 0.11 mm in setting was necessary?
    position reading problem  solved by mechanical fix to reduce the friction of the spring on LVDT
    change to potentiometer to avoid transducer problems  being considered
Beam size and jaw tilts: NOT measured
Set to nominal protect settings: DONE (theor. σ retraction)
Relative setting of TCDQ to TCSG: DONE

## Slide 12: TCDQ/TCSG set-up (III)
Check of TCDQ protection (dump of debunched beam):
  Losses concentrated on dump protection devices, with 0.1% on collimators
Beam1 losses
Beam2 losses
TCDS
TCDQ
TCP IR7
TCDQ
TCDS
Asynchronous dump tests:
4 bunches, B2
Sweep shape on BTVDD as expected

## Slide 13: How far did we get…
Injection Protection
Calibration of BLMs
Centering/beam size of TCDIs
Set TCDIs to 4.5 σ
Check phase space coverage
Check local MSI protection
TDI/TCLI centering/beam size with circulating beam
Set TDI/TCLI to ~7 σ
TDI/TCLI check against MKI failure
Dump Protection
Correct orbit in point 6
TCDQ – check SW interlock on beam position wrt TCDQ position
Set up TCDQ/TCS jaws
Check of TCDQ protection
Calibration of beam loss signal and protons lost at TCDQ
Aperture in P6

## Slide 14: Problem Summary
TCDI set up:
  losses in the ring already close to BLM interlock limit for pilot bunch…scraping in the SPS
  Ratio of one pilot bunch to one nominal SPS batch: 6.4e3
  BLM saturation and dump thresholds for fastest integration time scale – general issue for fast loss
  BLM crosstalk while set-up
TCDIs at.. | BLM: threshold/losses B1/B2 |  | 
 | 5e9 (B1/B2) | 1.6e10 | Nominal
4.5 σ hor/vert | 10/20 |  | 1·10-3/2·10-3
6.0 σ hor / 4.5 σ vert | 30/60 |  | 3·10-3/6·10-3
6.0 σ hor / 4.5 σ vert + SPS scraping |  | 103/105 | 10-1/10

## Slide 15: Problem Summary (II)
TDI asymmetry
  2mm offset in P8, to be understood, tank opening required
TCDQ
  reading problem  fix in shutdown
  7 mm misaligned for B1, being checked by experts
Overinjection B2: losses at MQXA (P8)
  to be solved…

## Slide 16: 3.5 TeV? Higher intensity?
NOT ready
Injection protection needs to be fully operational for maximum intensity of 1e12 per injection
Needs adequate setting-up time
TCDQ system should be tested for different β* squeeze steps
TCDQ system needs to be operational for stable beam

## Slide 17: 2010 Strategy
Refine procedure in view of what we learnt
Need to solve the issues listed
Get adequate commissioning time